## Sheet1
| SPRINTS | Summary | SEVERITY | EXPECTED Story Points | STATUS | [10 empty] | TOTAL Story Points(COMPLETED)
| SPRINT 5 (January 26, 2021 - February 23, 2021) | [8 empty] | January 26, 2021 - February 23, 2021
Issue Type | ID |  |  |  |  | 2021-01-26 | 2021-01-29 | 2021-02-01 | 2021-02-04 | 2021-02-07 | 2021-02-10 | 2021-02-13 | 2021-02-16 | 2021-02-19 | 2021-02-23
Story | ONCC-26e | As an Existing User, I want have a record of my saved code so that I can retrieve my saved code whenever required | HIGH | 8 | DONE | 0 | 1 | 2 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 8
Task | ONCC-27e | Aggregation of the Tabels for sharing code | HIGH | 0 | DONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | ONCC-28e | REST - API PUT, UPDATE, DELETE command | MEDIUM | 0 | DONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | ONCC-29e | Integration of DynamoDB + AWS | HIGH | 0 | DONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TOTAL HOURS | 8 |  | 0 | 1 | 2 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 8
|  |  |  | Actual Remaining Story Points | 8 | 8 | 7 | 5 | 4 | 3 | 2 | 2 | 1 | 0 | 0 | 0
|  |  |  | Estimated Remaining Story Points | 8 | 7.2 | 6.4 | 5.6 | 4.8 | 4 | 3.2 | 2.4 | 1.6 | 0.8 | 0 | 0