## Sheet1
| SPRINTS | Summary | SEVERITY | Expected Story Points | STATUS | [8 empty] | Toal Story Points(COMPLETED)
| SPRINT 6 (February 24, 2021 - March 16, 2021) | [8 empty] | SPRINT 6 (February 24, 2021 - March 16, 2021)
[6 empty] | 2021-02-24 | 2021-02-27 | 2021-03-02 | 2021-03-05 | 2021-03-08 | 2021-03-11 | 2021-03-14 | 2021-03-16
Issue type | ID |  | HIGHEST | 0 | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | ONCC-20 | Onboarded whole team on AWS | HIGHEST | 0 | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | ONCC-21 | Migration of MongoDB user table to DynamoDB part2 | MEDIUM | 0 | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | ONCC-23 | Installation of C module on system | MEDIUM | 0 | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | ONCC-24 | Get reference of C compiler using python pre-processing module | HIGHEST | 0 | DONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | ONCC-25 | Make a module to take pre-defined input from user | MEDIUM | 0 | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story | ONCC-26 | As a guest user I want to access a web application on cloud server so that I can compile code in any programming languages | HIGHEST | 4 | DONE | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Task | ONCC-28 | Update website design to make user friendly | LOW | 0 | IN PROGRESS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | ONCC-29 | Update technical paper for sprint 6 | MEDIUM | 0 | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | ONCC-30 | Update wiki page for sprint 6 | LOW | 0 | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | ONCC-31 | Create sprint 6 presentation slides | LOW | 0 | DONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | ONCC-35 | Update wiki page sprint 6 | LOW | 0 | DONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story | ONCC-36 | As a guest user I want to have C programming language option so that I can compile my code in C language | HIGHEST | 22 | IN PROGRESS | 3 | 2 | 3 | 2 | 2 | 3 | 2 | 0 | 17
Task | ONCC-48 | Merging C module with flask web application | MEDIUM | 0 | IN PROGRESS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | ONCC-49 | Connectivity between C module and web application | MEDIUM | 0 | IN PROGRESS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TOTAL HOURS | 26 |  | 5 | 4 | 3 | 2 | 2 | 3 | 2 | 0 | 21
|  |  |  | Actual Remaining Story Points | 26 | 21 | 17 | 14 | 12 | 10 | 7 | 5 | 5
|  |  |  | Estimated Remaining Story Points | 26 | 22.75 | 19.5 | 16.25 | 13 | 9.75 | 6.5 | 3.25 | 0