## Sheet1
| SPRINTS | TASKS | SEVERITY | EXPECTED HOURS | STATUS | [8 empty] | TOTAL HOURS(COMPLETED)
| SPRINT 1 (September 4, 2020 - September 18, 2020) | [7 empty] | (September 4, 2020 - September 18, 2020)
Issue-Type | ID | Summary |  |  |  | 2020-09-04 | 2020-09-06 | 2020-09-08 | 2020-09-10 | 2020-09-12 | 2020-09-14 | 2020-09-16 | 2020-09-18
Task | ONCC-1 | Research on project topics | MEDIUM | 20 | DONE | 7 | 3 | 4 | 2 | 3 | 0 | 1 | 0 | 20
Task | ONCC-2 | Requirement Gathering | HIGH | 10 | DONE | 0 | 0 | 5 | 0 | 2 | 3 | 0 | 0 | 10
Task | ONCC-3 | Discuss and Reasearch Database Design | MEDIUM | 6 | In Progress | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Task | ONCC-4 | Project Planning | HIGH | 8 | DONE | 2 | 0 | 2 | 0 | 0 | 2 | 2 | 0 | 8
Task | ONCC-5 | Task Allocation to each team member | LOW | 4 | DONE | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 4
|  |  | TOTAL HOURS(EXPECTED) | 48 |  | 10 | 5 | 11 | 2 | 5 | 5 | 4 | 3 | 45
|  |  |  | Actual Remaining Hrs | 48 | 38 | 33 | 22 | 20 | 15 | 10 | 6 | 3
|  |  |  | Estimated Remaining Hrs | 48 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0