## Sheet1
| SPRINTS |  | SEVERITY | EXPECTED HOURS | STATUS | [8 empty] | TOTAL HOURS(COMPLETED)
| SPRINT 3 (October 6, 2020 - October15, 2020) | [7 empty] | (October 6, 2020 - October 20, 2020)
Issue-Tyoe | ID | Summary |  |  |  | 2020-10-06 | 2020-10-08 | 2020-10-10 | 2020-10-12 | 2020-10-14 | 2020-10-16 | 2020-10-18 | 2020-10-20
Task | ONCC-11 | Initiate the Compiler module with Python | HIGH | 15 | DONE | 5 | 3 | 0 | 2 | 1 | 3 | 1 | 0 | 15
Task | ONCC-12 | Database Design | HIGH | 6 | DONE | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6
Task | ONCC-13 | Create Database tables for the user and registration | HIGH | 5 | DONE | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5
Task | ONCC-14 | Design Login Page | MEDUIM | 4 | DONE | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 4
Task | ONCC-15 | Design Registration Page | MEDUIM | 4 | DONE | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 4
Task | ONCC-16 | connection between web-appication and database | MEDUIM | 6 | DONE | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 6
Task | ONCC-17 | Initiate the REST API Development - GET Command | MEDUIM | 5 | DONE | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 2 | 5
|  |  | TOTAL HOURS | 45 |  | 14 | 5 | 1 | 5 | 6 | 7 | 3 | 4 | 45
|  |  |  | Actual Remaining Hrs | 45 | 31 | 26 | 25 | 20 | 14 | 7 | 4 | 0
|  |  |  | Expected Remaining Hrs | 45 | 39.375 | 33.75 | 28.125 | 22.5 | 16.875 | 11.25 | 5.625 | 0