## Sheet1
| SPRINTS | Summary | SEVERITY | EXPECTED Story Points | STATUS | [8 empty] | TOTAL Story Points(COMPLETED)
| SPRINT 4 (October 28, 2020 - November 16, 2020) | [7 empty] | (October 24, 2020 - November 20, 2020)
Issue Type | ID |  |  |  |  | 2020-10-24 | 2020-10-27 | 2020-10-30 | 2020-11-03 | 2020-11-06 | 2020-11-09 | 2020-11-13 | 2020-11-20
Task | ONCC-18 | Existing user Can not Re-register | MEDIUM | 0 | DONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story | ONCC-19 | As a Guest User, I want to have an option to select Java programming language so that I can compile my code written in Java language | HIGH | 8 | DONE | 1 | 1 | 2 | 1 | 1 | 2 | 0 | 0 | 8
Story | ONCC-20e | As a Registered User, I want to have a login page so that I can use features like save and edit existing code which are exclusively available for registered users only | HIGH | 2 | DONE | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2
Task | ONCC-21e | Decoding the password while comparing the password | HIGH | 0 | DONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | ONCC-22e | Initiate the Saving of Source Code module in front-end | HIGH | 0 | DONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | ONCC-23e | Create Table for saving source Code | HIGH | 0 | DONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | ONCC-24e | Aggregation of the Tabels for saving code to specific user | HIGH | 0 | DONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | ONCC-25e | REST - API PUT, UPDATE, DELETE command | MEDIUM | 0 | DONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | ONCC-26e | Create Session for each User after Login | HIGH | 0 | DONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TOTAL HOURS | 10 |  | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 0 | 10
|  |  |  | Actual Remaining Story Points | 10 | 9 | 8 | 6 | 5 | 4 | 1 | 0 | 0
|  |  |  | Estimated Remaining Story Points | 10 | 8.75 | 7.5 | 6.25 | 5 | 3.75 | 2.3 | 1.25 | 0